## slides
Risks (Failure Modes)
Requirements | Weight (req) | Requirements (incomplete, incorrect, ambiguous, changing) | Project Management (estimations, project, team management) | Technical (complex problem, lack of experience with technology) | Dependencies (on adjacent systems, components, other people) | Loss of Objective
Likelihood (risk) |  | 0.5 | 0.8 | 0.7 | 0.2
Creating a product that users would like | 0.7 | 0.9 | 0.3 | 0.9 | 0.5 | 0.994
Completing the product on time | 1 | 0.8 | 1 | 0.9 | 0.3 | 1
Risk Criticality |  | 0.715 | 0.968 | 1.071 | 0.13
R
PM
T
D

## Consequence
Risks (Failure Modes)
Requirements | Weight (req) |  | Loss of Objective
Likelihood (risk)
Risk Criticality

## Countermeasures
Risks (Failure Modes)
Countermeasures |  | Overall single effect of countermeasure
Criticality (risk)
Combined Risk Reduction