## Sheet1
[8 empty] | BBB | Bill | 10
[8 empty] | JJJ | Jill | 24
[8 empty] | PPP | Phil | 15
| 6 |  | 4
IT1 - BBB |  | IT3/IT4 - BBB
8
IT7 - JJJ
5
| 3 |  | 8 | [7 empty] | IT8 - JJJ
B2 - JJJ |  | IT2 - JJJ
[5 empty] | 2 |  |  |  | 4
|  |  |  | B6 - PPP |  |  |  | IT6 - PPP
| 5 |  | 4
IT5 - PPP |  | B7 - PPP
[7 empty] | ES | Earliest Start
[7 empty] | Dur | Duration
|  |  |  | ES | Dur | EF | EF | Earliest Finish
|  |  |  | Task_ID - Dev |  |  | Task_ID | Task Identifier
|  |  |  | LS | Flt | LF | Dev | Developer Assigned
[7 empty] | LS | Latest Start
[7 empty] | Flt | Float
[7 empty] | LF | Latest Finish

## Sheet2
| Initialize Earliest Start of Initial Tasks to 0 | [6 empty] | BBB | Bill | 10
[8 empty] | JJJ | Jill | 24
[8 empty] | PPP | Phil | 15
0 | 6 |  | 4
IT1 - BBB |  | IT3/IT4 - BBB
8
IT7 - JJJ
5
0 | 3 |  | 8 | [7 empty] | IT8 - JJJ
B2 - JJJ |  | IT2 - JJJ
[5 empty] | 2 |  |  |  | 4
|  |  |  | B6 - PPP |  |  |  | IT6 - PPP
0 | 5 |  | 4
IT5 - PPP |  | B7 - PPP
[7 empty] | ES | Earliest Start
[7 empty] | Dur | Duration
|  |  |  | ES | Dur | EF | EF | Earliest Finish
|  |  |  | Task_ID - Dev |  |  | Task_ID | Task Identifier
|  |  |  | LS | Flt | LF | Dev | Developer Assigned
[7 empty] | LS | Latest Start
[7 empty] | Flt | Float
[7 empty] | LF | Latest Finish

## Sheet3
| Calculate Earliest Finish for initial tasks | [7 empty] | BBB | Bill | 10
| EF = ES + Dur | [7 empty] | JJJ | Jill | 24
[9 empty] | PPP | Phil | 15
0 | 6 | 6 |  | 4
IT1 - BBB |  |  | IT3/IT4 - BBB
8
IT7 - JJJ
5
0 | 3 | 3 |  | 8 | [7 empty] | IT8 - JJJ
B2 - JJJ |  |  | IT2 - JJJ
[6 empty] | 2 |  |  |  | 4
[5 empty] | B6 - PPP |  |  |  | IT6 - PPP
0 | 5 | 5 |  | 4
IT5 - PPP |  |  | B7 - PPP
[8 empty] | ES | Earliest Start
[8 empty] | Dur | Duration
[5 empty] | ES | Dur | EF | EF | Earliest Finish
[5 empty] | Task_ID - Dev |  |  | Task_ID | Task Identifier
[5 empty] | LS | Flt | LF | Dev | Developer Assigned
[8 empty] | LS | Latest Start
[8 empty] | Flt | Float
[8 empty] | LF | Latest Finish

## Sheet4
| Calculate Earliest Start for IT3/IT4, IT2 and B7 | [7 empty] | BBB | Bill | 10
| ES = max EF of prerequisites | [7 empty] | JJJ | Jill | 24
[9 empty] | PPP | Phil | 15
0 | 6 | 6 | 6 | 4
IT1 - BBB |  |  | IT3/IT4 - BBB
8
IT7 - JJJ
5
0 | 3 | 3 | 6 | 8 | [7 empty] | IT8 - JJJ
B2 - JJJ |  |  | IT2 - JJJ
[6 empty] | 2 |  |  |  | 4
[5 empty] | B6 - PPP |  |  |  | IT6 - PPP
0 | 5 | 5 | 5 | 4
IT5 - PPP |  |  | B7 - PPP
[8 empty] | ES | Earliest Start
[8 empty] | Dur | Duration
[5 empty] | ES | Dur | EF | EF | Earliest Finish
[5 empty] | Task_ID - Dev |  |  | Task_ID | Task Identifier
[5 empty] | LS | Flt | LF | Dev | Developer Assigned
[8 empty] | LS | Latest Start
[8 empty] | Flt | Float
[8 empty] | LF | Latest Finish

## Sheet5
| Calculate Earliest Finish for IT3/IT4, IT2 and B7 | [8 empty] | BBB | Bill | 10
| EF = ES + Dur | [8 empty] | JJJ | Jill | 24
[10 empty] | PPP | Phil | 15
0 | 6 | 6 | 6 | 4 | 10
IT1 - BBB |  |  | IT3/IT4 - BBB
8
IT7 - JJJ
5
0 | 3 | 3 | 6 | 8 | 14 | [7 empty] | IT8 - JJJ
B2 - JJJ |  |  | IT2 - JJJ
[7 empty] | 2 |  |  |  | 4
[6 empty] | B6 - PPP |  |  |  | IT6 - PPP
0 | 5 | 5 | 5 | 4 | 9
IT5 - PPP |  |  | B7 - PPP
[9 empty] | ES | Earliest Start
[9 empty] | Dur | Duration
[6 empty] | ES | Dur | EF | EF | Earliest Finish
[6 empty] | Task_ID - Dev |  |  | Task_ID | Task Identifier
[6 empty] | LS | Flt | LF | Dev | Developer Assigned
[9 empty] | LS | Latest Start
[9 empty] | Flt | Float
[9 empty] | LF | Latest Finish

## Sheet6
| Calculate Earliest Start for IT7 and B6 | [8 empty] | BBB | Bill | 10
| ES = max EF of prerequisites | [8 empty] | JJJ | Jill | 24
[10 empty] | PPP | Phil | 15
0 | 6 | 6 | 6 | 4 | 10
IT1 - BBB |  |  | IT3/IT4 - BBB
[6 empty] | 14 | 8
IT7 - JJJ
5
0 | 3 | 3 | 6 | 8 | 14 | [7 empty] | IT8 - JJJ
B2 - JJJ |  |  | IT2 - JJJ
[6 empty] | 9 | 2 |  |  |  | 4
[6 empty] | B6 - PPP |  |  |  | IT6 - PPP
0 | 5 | 5 | 5 | 4 | 9
IT5 - PPP |  |  | B7 - PPP
[9 empty] | ES | Earliest Start
[9 empty] | Dur | Duration
[6 empty] | ES | Dur | EF | EF | Earliest Finish
[6 empty] | Task_ID - Dev |  |  | Task_ID | Task Identifier
[6 empty] | LS | Flt | LF | Dev | Developer Assigned
[9 empty] | LS | Latest Start
[9 empty] | Flt | Float
[9 empty] | LF | Latest Finish

## Sheet7
| Continue until all Early Start and Early Finish Times are Calculated | [8 empty] | BBB | Bill | 10
| ES = max EF of prerequisites | [8 empty] | JJJ | Jill | 24
| EF = ES + Dur | [8 empty] | PPP | Phil | 15
0 | 6 | 6 | 6 | 4 | 10
IT1 - BBB |  |  | IT3/IT4 - BBB | [7 empty] | Earliest Finish time for this project is 27
[6 empty] | 14 | 8 | 22
IT7 - JJJ
[13 empty] | 22 | 5 | 27
0 | 3 | 3 | 6 | 8 | 14 | [7 empty] | IT8 - JJJ
B2 - JJJ |  |  | IT2 - JJJ
[6 empty] | 9 | 2 | 11 |  | 11 | 4 | 15
[6 empty] | B6 - PPP |  |  |  | IT6 - PPP
0 | 5 | 5 | 5 | 4 | 9
IT5 - PPP |  |  | B7 - PPP
[9 empty] | ES | Earliest Start
[9 empty] | Dur | Duration
[6 empty] | ES | Dur | EF | EF | Earliest Finish
[6 empty] | Task_ID - Dev |  |  | Task_ID | Task Identifier
[6 empty] | LS | Flt | LF | Dev | Developer Assigned
[9 empty] | LS | Latest Start
[9 empty] | Flt | Float
[9 empty] | LF | Latest Finish

## Sheet8
| Initialize latest finish of IT8 to its earliest finish time | [8 empty] | BBB | Bill | 10
[10 empty] | JJJ | Jill | 24
[10 empty] | PPP | Phil | 15
0 | 6 | 6 | 6 | 4 | 10
IT1 - BBB |  |  | IT3/IT4 - BBB
[6 empty] | 14 | 8 | 22
IT7 - JJJ
[13 empty] | 22 | 5 | 27
0 | 3 | 3 | 6 | 8 | 14 | [7 empty] | IT8 - JJJ
B2 - JJJ |  |  | IT2 - JJJ | [11 empty] | 27
[6 empty] | 9 | 2 | 11 |  | 11 | 4 | 15
[6 empty] | B6 - PPP |  |  |  | IT6 - PPP
0 | 5 | 5 | 5 | 4 | 9
IT5 - PPP |  |  | B7 - PPP
[9 empty] | ES | Earliest Start
[9 empty] | Dur | Duration
[6 empty] | ES | Dur | EF | EF | Earliest Finish
[6 empty] | Task_ID - Dev |  |  | Task_ID | Task Identifier
[6 empty] | LS | Flt | LF | Dev | Developer Assigned
[9 empty] | LS | Latest Start
[9 empty] | Flt | Float
[9 empty] | LF | Latest Finish

## Sheet9
| Finish Calculations for IT8 | [8 empty] | BBB | Bill | 10
| Flt = LF - EF | [8 empty] | JJJ | Jill | 24
| LS = LF - Dur | [8 empty] | PPP | Phil | 15
0 | 6 | 6 | 6 | 4 | 10
IT1 - BBB |  |  | IT3/IT4 - BBB
[6 empty] | 14 | 8 | 22
IT7 - JJJ
[13 empty] | 22 | 5 | 27
0 | 3 | 3 | 6 | 8 | 14 | [7 empty] | IT8 - JJJ
B2 - JJJ |  |  | IT2 - JJJ | [9 empty] | 22 | 0 | 27
[6 empty] | 9 | 2 | 11 |  | 11 | 4 | 15
[6 empty] | B6 - PPP |  |  |  | IT6 - PPP
0 | 5 | 5 | 5 | 4 | 9
IT5 - PPP |  |  | B7 - PPP
[9 empty] | ES | Earliest Start
[9 empty] | Dur | Duration
[6 empty] | ES | Dur | EF | EF | Earliest Finish
[6 empty] | Task_ID - Dev |  |  | Task_ID | Task Identifier
[6 empty] | LS | Flt | LF | Dev | Developer Assigned
[9 empty] | LS | Latest Start
[9 empty] | Flt | Float
[9 empty] | LF | Latest Finish

## Sheet10
| Calculate Latest Finish for IT7 and IT6 | [8 empty] | BBB | Bill | 10
| LF = min of dependent's latest start (LS) | [8 empty] | JJJ | Jill | 24
[10 empty] | PPP | Phil | 15
0 | 6 | 6 | 6 | 4 | 10
IT1 - BBB |  |  | IT3/IT4 - BBB
[6 empty] | 14 | 8 | 22
IT7 - JJJ
[8 empty] | 22 |  |  |  |  | 22 | 5 | 27
0 | 3 | 3 | 6 | 8 | 14 | [7 empty] | IT8 - JJJ
B2 - JJJ |  |  | IT2 - JJJ | [9 empty] | 22 | 0 | 27
[6 empty] | 9 | 2 | 11 |  | 11 | 4 | 15
[6 empty] | B6 - PPP |  |  |  | IT6 - PPP
22
0 | 5 | 5 | 5 | 4 | 9
IT5 - PPP |  |  | B7 - PPP
[9 empty] | ES | Earliest Start
[9 empty] | Dur | Duration
[6 empty] | ES | Dur | EF | EF | Earliest Finish
[6 empty] | Task_ID - Dev |  |  | Task_ID | Task Identifier
[6 empty] | LS | Flt | LF | Dev | Developer Assigned
[9 empty] | LS | Latest Start
[9 empty] | Flt | Float
[9 empty] | LF | Latest Finish

## Sheet11
| Finish Calculations for IT7 and IT6 | [8 empty] | BBB | Bill | 10
| Flt = LF - EF | [8 empty] | JJJ | Jill | 24
| LS = LF - Dur | [8 empty] | PPP | Phil | 15
0 | 6 | 6 | 6 | 4 | 10
IT1 - BBB |  |  | IT3/IT4 - BBB
[6 empty] | 14 | 8 | 22
IT7 - JJJ
[6 empty] | 14 | 0 | 22 |  |  |  |  | 22 | 5 | 27
0 | 3 | 3 | 6 | 8 | 14 | [7 empty] | IT8 - JJJ
B2 - JJJ |  |  | IT2 - JJJ | [9 empty] | 22 | 0 | 27
[6 empty] | 9 | 2 | 11 |  | 11 | 4 | 15
[6 empty] | B6 - PPP |  |  |  | IT6 - PPP
[10 empty] | 18 | 7 | 22
0 | 5 | 5 | 5 | 4 | 9
IT5 - PPP |  |  | B7 - PPP
[9 empty] | ES | Earliest Start
[9 empty] | Dur | Duration
[6 empty] | ES | Dur | EF | EF | Earliest Finish
[6 empty] | Task_ID - Dev |  |  | Task_ID | Task Identifier
[6 empty] | LS | Flt | LF | Dev | Developer Assigned
[9 empty] | LS | Latest Start
[9 empty] | Flt | Float
[9 empty] | LF | Latest Finish

## Sheet12
| Calculate Latest Finish for B6, IT3/IT4, IT2 | [8 empty] | BBB | Bill | 10
| LF = min of dependent's latest start (LS) | [8 empty] | JJJ | Jill | 24
[10 empty] | PPP | Phil | 15
0 | 6 | 6 | 6 | 4 | 10
IT1 - BBB |  |  | IT3/IT4 - BBB
[5 empty] | 14 | 14 | 8 | 22
IT7 - JJJ
[6 empty] | 14 | 0 | 22 |  |  |  |  | 22 | 5 | 27
0 | 3 | 3 | 6 | 8 | 14 | [7 empty] | IT8 - JJJ
B2 - JJJ |  |  | IT2 - JJJ | [9 empty] | 22 | 0 | 27
[5 empty] | 14 | 9 | 2 | 11 |  | 11 | 4 | 15
[6 empty] | B6 - PPP |  |  |  | IT6 - PPP
[8 empty] | 18 |  | 18 | 7 | 22
0 | 5 | 5 | 5 | 4 | 9
IT5 - PPP |  |  | B7 - PPP
[9 empty] | ES | Earliest Start
[9 empty] | Dur | Duration
[6 empty] | ES | Dur | EF | EF | Earliest Finish
[6 empty] | Task_ID - Dev |  |  | Task_ID | Task Identifier
[6 empty] | LS | Flt | LF | Dev | Developer Assigned
[9 empty] | LS | Latest Start
[9 empty] | Flt | Float
[9 empty] | LF | Latest Finish

## Sheet13
| Finish calculatations for B6, IT3/IT4, IT2 | [8 empty] | BBB | Bill | 10
| Flt = LF - EF | [8 empty] | JJJ | Jill | 24
| LS = LF - Dur | [8 empty] | PPP | Phil | 15
0 | 6 | 6 | 6 | 4 | 10
IT1 - BBB |  |  | IT3/IT4 - BBB
|  |  | 10 | 4 | 14 | 14 | 8 | 22
IT7 - JJJ
[6 empty] | 14 | 0 | 22 |  |  |  |  | 22 | 5 | 27
0 | 3 | 3 | 6 | 8 | 14 | [7 empty] | IT8 - JJJ
B2 - JJJ |  |  | IT2 - JJJ | [9 empty] | 22 | 0 | 27
|  |  | 6 | 0 | 14 | 9 | 2 | 11 |  | 11 | 4 | 15
[6 empty] | B6 - PPP |  |  |  | IT6 - PPP
[6 empty] | 16 | 7 | 18 |  | 18 | 7 | 22
0 | 5 | 5 | 5 | 4 | 9
IT5 - PPP |  |  | B7 - PPP
[9 empty] | ES | Earliest Start
[9 empty] | Dur | Duration
[6 empty] | ES | Dur | EF | EF | Earliest Finish
[6 empty] | Task_ID - Dev |  |  | Task_ID | Task Identifier
[6 empty] | LS | Flt | LF | Dev | Developer Assigned
[9 empty] | LS | Latest Start
[9 empty] | Flt | Float
[9 empty] | LF | Latest Finish

## Sheet14
| Calculate Latest Finish for IT1,B2 and B7 | [8 empty] | BBB | Bill | 10
| LF = min of dependent's latest start (LS) | [8 empty] | JJJ | Jill | 24
[10 empty] | PPP | Phil | 15
0 | 6 | 6 | 6 | 4 | 10
IT1 - BBB |  |  | IT3/IT4 - BBB
|  | 6 | 10 | 4 | 14 | 14 | 8 | 22
IT7 - JJJ
[6 empty] | 14 | 0 | 22 |  |  |  |  | 22 | 5 | 27
0 | 3 | 3 | 6 | 8 | 14 | [7 empty] | IT8 - JJJ
B2 - JJJ |  |  | IT2 - JJJ | [9 empty] | 22 | 0 | 27
|  | 6 | 6 | 0 | 14 | 9 | 2 | 11 |  | 11 | 4 | 15
[6 empty] | B6 - PPP |  |  |  | IT6 - PPP
[6 empty] | 16 | 7 | 18 |  | 18 | 7 | 22
0 | 5 | 5 | 5 | 4 | 9
IT5 - PPP |  |  | B7 - PPP
14
[9 empty] | ES | Earliest Start
[9 empty] | Dur | Duration
[6 empty] | ES | Dur | EF | EF | Earliest Finish
[6 empty] | Task_ID - Dev |  |  | Task_ID | Task Identifier
[6 empty] | LS | Flt | LF | Dev | Developer Assigned
[9 empty] | LS | Latest Start
[9 empty] | Flt | Float
[9 empty] | LF | Latest Finish

## Sheet15
| Finish calculatations for IT1, B2 and B7 | [8 empty] | BBB | Bill | 10
| Flt = LF - EF | [8 empty] | JJJ | Jill | 24
| LS = LF - Dur | [8 empty] | PPP | Phil | 15
0 | 6 | 6 | 6 | 4 | 10
IT1 - BBB |  |  | IT3/IT4 - BBB
0 | 0 | 6 | 10 | 4 | 14 | 14 | 8 | 22
IT7 - JJJ
[6 empty] | 14 | 0 | 22 |  |  |  |  | 22 | 5 | 27
0 | 3 | 3 | 6 | 8 | 14 | [7 empty] | IT8 - JJJ
B2 - JJJ |  |  | IT2 - JJJ | [9 empty] | 22 | 0 | 27
3 | 3 | 6 | 6 | 0 | 14 | 9 | 2 | 11 |  | 11 | 4 | 15
[6 empty] | B6 - PPP |  |  |  | IT6 - PPP
[6 empty] | 16 | 7 | 18 |  | 18 | 7 | 22
0 | 5 | 5 | 5 | 4 | 9
IT5 - PPP |  |  | B7 - PPP
|  |  | 10 | 5 | 14
[9 empty] | ES | Earliest Start
[9 empty] | Dur | Duration
[6 empty] | ES | Dur | EF | EF | Earliest Finish
[6 empty] | Task_ID - Dev |  |  | Task_ID | Task Identifier
[6 empty] | LS | Flt | LF | Dev | Developer Assigned
[9 empty] | LS | Latest Start
[9 empty] | Flt | Float
[9 empty] | LF | Latest Finish

## Sheet16
| Continue… | [8 empty] | BBB | Bill | 10
| LF = min of dependent's latest start (LS) | [8 empty] | JJJ | Jill | 24
| Flt = LF - EF |  | LS = LF - Dur | [6 empty] | PPP | Phil | 15
0 | 6 | 6 | 6 | 4 | 10
IT1 - BBB |  |  | IT3/IT4 - BBB
0 | 0 | 6 | 10 | 4 | 14 | 14 | 8 | 22
IT7 - JJJ
[6 empty] | 14 | 0 | 22 |  |  |  |  | 22 | 5 | 27
0 | 3 | 3 | 6 | 8 | 14 | [7 empty] | IT8 - JJJ
B2 - JJJ |  |  | IT2 - JJJ | [9 empty] | 22 | 0 | 27
3 | 3 | 6 | 6 | 0 | 14 | 9 | 2 | 11 |  | 11 | 4 | 15
[6 empty] | B6 - PPP |  |  |  | IT6 - PPP
[6 empty] | 16 | 7 | 18 |  | 18 | 7 | 22
0 | 5 | 5 | 5 | 4 | 9
IT5 - PPP |  |  | B7 - PPP
5 | 5 | 10 | 10 | 5 | 14
[9 empty] | ES | Earliest Start
[9 empty] | Dur | Duration
[6 empty] | ES | Dur | EF | EF | Earliest Finish
[6 empty] | Task_ID - Dev |  |  | Task_ID | Task Identifier
[6 empty] | LS | Flt | LF | Dev | Developer Assigned
[9 empty] | LS | Latest Start
[9 empty] | Flt | Float
[9 empty] | LF | Latest Finish

## Sheet17
| Label the Critical Path, i.e. mark nodes with no float time | [8 empty] | BBB | Bill | 10
| Related properties of these nodes are ES==LS and EF==LF | [8 empty] | JJJ | Jill | 24
[10 empty] | PPP | Phil | 15
0 | 6 | 6 | 6 | 4 | 10
IT1 - BBB |  |  | IT3/IT4 - BBB
0 | 0 | 6 | 10 | 4 | 14 | 14 | 8 | 22
IT7 - JJJ
[6 empty] | 14 | 0 | 22 |  |  |  |  | 22 | 5 | 27
0 | 3 | 3 | 6 | 8 | 14 | [7 empty] | IT8 - JJJ
B2 - JJJ |  |  | IT2 - JJJ | [9 empty] | 22 | 0 | 27
3 | 3 | 6 | 6 | 0 | 14 | 9 | 2 | 11 |  | 11 | 4 | 15
[6 empty] | B6 - PPP |  |  |  | IT6 - PPP
[6 empty] | 16 | 7 | 18 |  | 18 | 7 | 22
0 | 5 | 5 | 5 | 4 | 9
IT5 - PPP |  |  | B7 - PPP
5 | 5 | 10 | 10 | 5 | 14
[9 empty] | ES | Earliest Start
[9 empty] | Dur | Duration
[6 empty] | ES | Dur | EF | EF | Earliest Finish
[6 empty] | Task_ID - Dev |  |  | Task_ID | Task Identifier
[6 empty] | LS | Flt | LF | Dev | Developer Assigned
[9 empty] | LS | Latest Start
[9 empty] | Flt | Float
[9 empty] | LF | Latest Finish